## Timeline Tool
Timeline Tool - Video Enabled Care (VEC) Implementation
Service :
|  |  | Project Start Date: | 00/00/2024
| For further information please email virtualhealth@hse.ie |  | Approx Schedule End Date: (7 weeks) | 00/00/2024
WBS | Task | Project Status (Dropdown Below) | Assigned To | Start | Duration (Days)
1 | Engage and Plan
1.1 | Complete project brief |  | Joe Bloggs | 10.10.2020 | 3 | Not started
1.1.1 | Project brief manager sign off | Not started |  |  |  | In progress
1.2 | Identify and engage with key stakeholders - Complete Stakeholders tab below | In progress |  | 2022-02-14 | 3 | High Priority
1.3 | Set up working group – complete working group tab below | High Priority |  |  |  | Complete
1.3.1 | Organise weekly meetings with working group | Complete
1.4 | Include video as a standing item on agendas
1.5 | Identify Initial service area to begin with | In progress |  | 2022-02-07
1.6 | Assess scope and scale for video usage
1.7 | Seek shared learning |  |  | 2022-02-07
1.8 | Review change management guide
1.8.1 | Identify a framework for gathering evidence
1.9 | Identify potential risks - complete the tab below
1.9.1 | Circulate implementation Toolkit to all necessay stakeholders
1.10. | Stakeholder roles & responsibilities tab complete
1.11 | Status update meeting with key stakeholders and working group inc. progress to date
2 | Identify Opportunities & Review processes
2.1 | Review existing process
2.1.1 | Map existing process (NB - engage with necessary stakholders)
2.1.2 | Map Future state process
2.2 | Identify video opportunities within existing process
2.3 | Update templates/SOP/Leaflet/Poster
2.4 | Identify suitable platform for VEC opportunities
2.5 | Identify contingency plan if video fails | Complete |  | 2022-02-07
2.6 | Have you considered how to record patient consent
2.6.1 | Review National Consent Policy
2.6.2 | Agree a process in line with existing on how to record patient consent
2.7 | Define eligibility criteria for suitable patient - clinican led
2.8 | Identify how patients will be offered/request an online health appointment
2.9 | Agree what information is to be given to the patient with the appointment link - Link on HSE national website, patient support page is very helpful
3 | Where, What & How Checklist
3.1 | Identify the location where VEC will take place
3.2 | Review hardware and equipment available |  |  | 2022-02-07
3.2.1 | Review hardware and equipment required |  |  | 2022-02-07
3.2.2 | Order hardware and equipment required
3.3 | Review types of VEC your service will facilitate from process map
3.4 | Agree and select video tool/s of choice in line with video opportunities
3.5 | Request email set up for staff who dont have email address (if applicable) | High Priority
3.5.1 | Apply for video tool licenses
3.5.2 | Schedule initial group training (champions/super users) - small group or watch/read training material available (Train a trainer approach)
3.5.3 | Trial platform/s among peers as clinician/patient before using with patient
3.5.4 | Practice/Trial/Test
3.6 | Schedule presentation with all staff
3.7 | Schedule training with all relevant staff (Train a trainer)
3.8 | Champions/Super users to support all staff
3.9 | Communicate use of video and create awareness - Display poster/brochures/website/pullup stand
3.10. | Status update meeting with key stakeholders and working group inc. progress to date
4 | Go Live & Sustainability
4.1 | Finalise workflows, SOPs, templates, letters, suitability critera
4.2 | Finalise information service users need
Go Live Group 1 - internal & select patient
4.8 | Review readness and confidence before going out to the patient
4.9 | Status update meeting with key stakeholders and working group inc. progress to date
4.10. | Practice/Trial/Test
4.11 | Go Live Group 2 - small patient cohort
4.12 | Evaluate and Lessons Learned
4.12.1 | Review evidence captured
4.16 | Go Live Group 3 - scale up
5 | Readiness Checklist
5.1 | Planning complete
5.2 | Processes amended
5.3 | Processes reviewed
5.4 | Appropriate Environment identified
5.5 | Technology review complete
5.6 | Training & testing complete
5.7 | Trialing and Testing complete
5.8 | Review evidence captured
5.9 | Implementation complete | Complete
6 | Sustainability and embedding
6.1 | Review 3 months/6 months/1 year
6.2 | Project Close
6.3 | Record Decisions/data | High Priority
6.3.1 | Analyse and share data evidence
6.4 | Communicate to Stakeholders | Not started
6.5 | Project Evaluation and Lessons Learned
6.6 | Review 6 month | In Progress
6.7 | Evaluation/Lessons learned Meeting
6.8 | Review 1 year
To add more data, Insert new rows ABOVE this one

## Working Group
Name | Title | Role

## Roles & Responsibilities
Role | Representative | Responsibilities
Service Implementation Lead |  | • To provide leadership, co-ordination and change management, within their service, in implementing/embedding and using video consultation platforms in line with the implementation framework. • To empower, motivate, support, and advise staff throughout the project and create a sustainable model which will ensure a blended care approach to healthcare into the future. • Gather data evidence which will become available nationally.
Working Group (Complete working group tab within timeline tool including roles within group) |  | Group led by the Project Lead responsible for making collaborative decisions and ongoing progression of the video implementation supporting sustainability Identify and agree appropriate processes to progress the project within the agreed timeframe • Membership should reflect a core representation from all MDT and administrative support involved in the project implementation. • Members should actively participate through attendance, discussion, review of minutes, papers and other working group documents. • Members should support open discussion and debate within the group and complete agreed tasks within the allocated timeframes. • Members are responsible for the dissemination of information and the positive communication of the agreed digital change projects among the staff they represent.
Implementation team = Service implementation Lead and Working group members
CHO Digital Health Team / Hospital IT/ equivalent |  | • To provide project management and support to Project Leads, in embeding, management and use of video consultation platforms, utilising the implementation toolkit, including; post implementation project support and follow up. • Provide advice on use of video consultation platforms and associated audio-visual hardware to enable staff to engage with both video and teleconference platforms, in light of demand for clinics/consults/services/clinical meetings/professional development forums to be delivered remotely. • Signpost services to required resources to enable,empower and develop local linkages ensuring shared learning • Promoting the gathering of data evidence and use cases which will become available nationally
Telehealth Programme Team – eHealth |  | • Provide assistance to the local digital health teams supporting them to deliver on video solutions within the HSE and wider healthcare services. • Management of AttendAnywhere platform, supply of equipment to enable video enabled care and support the projects infrastructure and technical requirements. • Provide national status reporting to the Telehealth Steering Group on video implementations nationally. • Facilitate and coordinate the collation of data evidence nationally and communicate to the correct stakeholders.
Nursing/Midwifery Planning & Development Unit (NMPDU) |  | • Engage with Nursing & Midwifery Colleagues to provide guidance on the implementation and optimisation of VEC opportunities as part of the project implementation plan • Sign post and support educational opportunities in digital skills and VEC training such as exemplar webinars, use case sharing and research opportunities in Nursing & Midwifery • Support the development of national resources and supports including policies, procedures, protocols, guidelines and implementation guides to support Video enabled Care implementation and sustainability • Build communities of VEC practice and peer support to build confidence in the nursing and midwifery workforce • Support the evaluation of the implementation of VEC , through guidance and the availability of evaluation tools

## Risks
Risk Assesment | [6 empty] | Risk Possibilities
Identified Risk | Category | Impact (Low-Med-high) | Probability | Mitigaton | Responsible Person | Status (Open/Closed) | Lack of commitment and enagement from working group
Resistence from stakeholders
|  | Low |  |  |  |  | Resistence to change
|  | High |  |  |  |  | Technology issues/ Site infrastructure
|  | High |  |  |  |  | Resource Risks – Lack of availability of staff for planning, training, and coordination
|  | Low |  |  |  |  | Organizational Risks - Senior Management Support
Medium

## IssueLog
Issue Log
Identified Issue | Issue Oveview | Impact (Low-Med-high) | Responsible Person | Actionee | Status (Open/Closed) | Resolution Notes
High
Medium
Low